## Full Timeline
2022 NCF-Envirothon Deliverables | Date Due | Task Lead | Committee | Completed (yes/no)
January 1, 2021-August 31, 2021
Submit Final Host Proposal to NCFE | February | Host | Logistics | yes
NCF accepts proposal | February | NCF |  | yes
Host establishs Committee and Subcommittees | Immediately | Host | Logistics
Event length determination and chair(s) named | Immediately | Host | Logistics
Develop fundraising plan | Immediately | Host/NCFE | Logistics
Enter MOU between NCF and Host Committee | February | Host/NCFE |  | yes
First draft of CEI (fifth station topic) reference material packet & learning objectives due to the NCFE for review (200 pages max) | 2021-05-01 | Host | Education
First draft of site-specific resource materials/learning objectives for all 5 stations due to NCFE for review(100 pages max. per station) | 2021-05-01 | Host | Education
Second draft of CEI (fifth station topic) reference material packet & learning objectives due to the NCFE for review (200 pages max) | 2021-07-15 | Host | Education
Second draft of site-specific resource materials/learning objectives for all 5 stations due to NCFE for review (100 pages max. per station) | 2021-07-15 | Host | Education
Facilities and locations visited by NCFE | spring/summer | Host/NCFE
Presentation of Event Location and Theme to NCFEOC at Summer meeting of representatives | summer | Host | Logistics
September 1, 2021-Dec 31, 2021
Begin monthly 2022 Host Meetins (Host planning committee members, NCFE staff, select NCFEOC members) | September | Host/NCFE
Final (3rd) draft of CEI (fifth station topic) reference material packet & learning objectives due to the NCFE for approval (200 pages max) | 2021-09-01 | Host | Education
Final (3rd) Draft of site-specific resource materials/learning objectives for all 5 stations due to NCFE for approval (100 pages max. per station) | 2021-09-01 | Host | Education
CEI (fifth station topic) reference material packet & learning objectives posted to NCFE website | 2021-09-15 | NCFE
First Draft of Communications Plan due to NCFE for review | 2021-10-01 | Host | Communication
First Draft of all 5 Station Tests due to NCFE for review | 2021-11-01 | Host | Education
First Draft Oral Presentation Scenario due to NCFE for review | 2021-11-01 | Host | Education
January 1, 2022-August 31, 2022
Registration fees (teams, guests, other fees) finalized | 2022-01-15 | Host/NCFE | Logistics
Draft of Oral Presentation Rules and Guidelines due to NCFE for review by NCFEOC at winter meeting | 2022-01-15 | Host | Education
First Draft of 2022 Event Guide due to NCFE for review | 2022-01-15 | Host | Communications
Second Draft of all 5 Station Tests due to NCFE for review | 2022-01-30 | Host | Education
Second Draft Oral Presentation Scenario due to NCFE for review | 2022-01-30 | Host | Education
First draft of all 5 station training & OP scenario training plan due to NCFE for review | 2022-01-30 | Host | Education
Signed contract(s) with event locations (i.e. University &/or others) regarding housing, food, transportation, meeting rooms, etc. Copies to be provided to NCFE | 2022-01-30 | Host | Logistics
Team Registration - payment option open to state/provincial/partner nations | 2022-02-01 | NCFE | Logistics
Second draft of Communications Plan due to NCFE for review | 2022-02-01 | Host | Communications
2022 NCFEOC Winter Meeting | early February | Host/NCFE
Oral Presentation Rules and Guidelines posted to NCFE website & emailed to state/provincial Reps | 2022-02-15 | NCFE
List of Oral Presentation judges due to NCFE for review (preliminary and top 3 judges); name and area of expertise | 2022-03-01 | Host | Education
Second draft of 2022 Event Guide due to NCFE for review | 2022-03-01 | Host | Communications
Final draft of Communications Plan due to NCFE for implementation | 2022-03-01 | Host | Communications
Final draft of 2022 Event Guide due to NCFE for approval (ready to post to web on 4/15/22) | 2022-04-01 |  | Communications
Full 2022 Registration open (team member names/information, Guest registrations & others) | 2022-04-15 | NCFE
2022 Event Guide posted to NCFE website | 2022-04-15 | NCFE
Emergency Procedures Plan due to NCFE | 2022-04-15 | Host | Logistics
Site-specific resource materials/learning objectives for all topics posted to NCFE website | 2022-05-01 | NCFE
Proof of event insurance copies to NCFE | 2022-05-01 | Host | Logistics
Invitation to VIP guests (sponsors, partners, etc.) to participate in Opening/Closing ceremonies | 2022-05-01 | Host/NCF | Logistics/ Communication
Final (3rd) draft of all 5 Station Test due to NCFE for approval | 2022-05-01 | Host | Education
Final draft of Oral Presentation Scenario due to NCFE for approval | 2022-05-01 | Host | Education
Final draft of all 5 Stations Training & OP scenario training plans due to NCFE for approval | 2022-05-01 | Host | Education
First draft Opening and Closing program agendas due to NCFE for approval | 2022-06-01 | Host/NCFE | Communications
All Registration forms and fees due to NCFE | 2022-06-15 | NCFE | Logistics
First registration fee payment to Host (up to 50 percent of registration fees collected) | 2022-06-30 | NCF
Final draft Opening and Closing program agendas due to NCFE for approval | 2022-07-01 | Host/NCFE | Communications
Host 2022 Event | July 24-30, 2022 | Host/NCFE
Thank you letters to all Sponsors | 8/1/2022 - 8/15/2022 | Host/NCFE | Logistics/ Communication
Second registration fee payment to Host (up to additional 40 percent of remainder of registration fees collected) | 2022-08-15 | NCF
Year Following Competition | September 1, 2022 - March 1, 2023
Final financial report to NCF fifteen (15) days prior to the NCF winter meeting | ~January 15, 2023 | Host | Logistics
Wrap up presentation to NCFEOC at Winter meeting | early February | Host | Logistics
Final Registration Fee payment due to Host (2/15/22 or within 30 days of receipt of the Final financial report) | ~ February 15, 2020 | NCF
Notes:
Bold text = item w/ deadlines that are not flexible
Logistics Committee - charged with general event logistics, coordination, etc.
Education Committee - charged with developing all educational content and tests and organizing the testing/training/OP portions of event
PR/Communications Committee - charged with communications/PR before, during and after event

## Logistics
Operations Committee | Date Due | Task Lead | Completed (yes/no)
January 1, 2021-August 31, 2021
Submit Final Host Proposal to NCFE | February | Host | yes
NCF accepts proposal | February | NCF | yes
Host establish Committee and Subcommittees | Immediately | Host
Event length determination and chair(s) named | Immediately | Host
Develop fundraising plan | Immediately | Host/NCFE
Enter MOU between NCF and Host Committee | February | Host/NCFE | yes
Facilities and locations visited by NCFE | spring/summer | NCFE
Presentation of Event Location and Theme to NCFEOC at Summer meeting of representatives | summer | Host
September 1, 2021-Dec 31, 2021
Begin monthly 2022 Host Meetins (Host planning committee members, NCFE staff, select NCFEOC members) | September | Host/NCFE
January 1, 2022-August 31, 2022
Registration fees (teams, guests, other fees) finalized | 2022-01-15 | Host/NCFE
Signed contract(s) with event locations (i.e. University &/or others) regarding housing, food, transportation, meeting rooms, etc. Copies to be provided to NCFE | 2022-01-30 | Host
Team Registration payment - open to state/provincial/partner nations | 2022-02-01 | NCFE
2022 NCFEOC Winter Meeting | early February
Full 2022 Registration open (team member names/information, Guest registrations & others) | 2022-04-15 | NCFE
Emergency Procedures Plan due to NCFE | 2022-04-15 | Host
Proof of event insurance copies to NCFE | 2022-05-01 | Host
Invitation to VIP guests (sponsors, partners, etc.) to participate in Opening/Closing ceremonies | 2022-05-01 | Host/NCF
All Registration forms and fees due to NCFE | 2022-06-15 | NCFE
Host 2022 Event | July 24-30, 2022 | Host/NCFE
Thank you letters to all Sponsors | 8/1/2022 - 8/15/2022 | Host/NCFE
Year Following Competition | September 1, 2022 - March 1, 2023
Final financial statement to NCF fifteen (15) days prior to the NCF winter meeting | ~January 15, 2023 | Host
Wrap up presentation to NCFEOC at Winter meeting | early February | Host

## Education
Education Committee | Date Due | Task Lead | Completed (yes/no)
January 1, 2021-August 31, 2021
First draft of CEI (fifth station topic) reference material packet & learning objectives due to the NCFE for review (200 pages max) | 2021-05-01 | Host
First draft of site-specific resource materials/learning objectives for all 5 stations due to NCFE for review(100 pages max. per station) | 2021-05-01 | Host
Second draft of CEI (fifth station topic) reference material packet & learning objectives due to the NCFE for review (200 pages max) | 2021-07-15 | Host
Second draft of site-specific resource materials/learning objectives for all 5 stations due to NCFE for review (100 pages max. per station) | 2021-07-15 | Host
September 1, 2021-Dec 31, 2021
Begin monthly 2022 Host Meetins (Host planning committee members, NCFE staff, select NCFEOC members) | September | Host/NCFE
Final (3rd) draft of CEI (fifth station topic) reference material packet & learning objectives due to the NCFE for approval (200 pages max) | 2021-09-01 | Host
Final (3rd) Draft of site-specific resource materials/learning objectives for all 5 stations due to NCFE for approval (100 pages max. per station) | 2021-09-01 | Host
CEI (fifth station topic) reference material packet & learning objectives posted to NCFE website | 2021-09-15 | NCFE
First Draft of all 5 Station Tests due to NCFE for review | 2021-11-01 | Host
First Draft Oral Presentation Scenario due to NCFE for review | 2021-11-01 | Host
January 1, 2022-August 31, 2022
Draft of Oral Presentation Rules and Guidelines due to NCFE for review by NCFEOC at winter meeting | 2022-01-15 | Host
Second Draft of all 5 Station Tests due to NCFE for review | 2022-01-30 | Host
Second Draft Oral Presentation Scenario due to NCFE for review | 2022-01-30 | Host
First draft of all 5 station training & OP scenario training plan due to NCFE for review | 2022-01-30 | Host
Oral Presentation Rules and Guidelines posted to NCFE website & emailed to state/provincial Reps | 2022-02-15 | NCFE
List of Oral Presentation judges due to NCFE for review (preliminary and top 3 judges); name and area of expertise | 2022-03-15 | Host
Site-specific resource materials/learning objectives for all topics posted to NCFE website | 2022-05-01 | NCFE
Final (3rd) draft of all 5 Station Test due to NCFE for approval | 2022-05-01 | Host
Final draft of all 5 Stations Training & OP scenario training plans due to NCFE for approval | 2022-05-01 | Host
Final draft of Oral Presentation Scenario due to NCFE for approval | 2022-05-01 | Host
Host 2022 Event | July 24-30, 2022 | Host/NCFE
Year Following Competition | September 1, 2022 - March 1, 2023

## PR-Communications
Communications Committee | Date Due | Task Lead | Completed (yes/no)
January 1, 2021-August 31, 2021
September 1, 2021-Dec 31, 2021
Begin monthly 2022 Host Meetins (Host planning committee members, NCFE staff, select NCFEOC members) | September | Host/NCFE
First Draft of Communications Plan due to NCFE for review | 2021-10-01 | Host
January 1, 2022-August 31, 2022
First Draft of 2022 Event Guide due to NCFE for review | 2022-01-15 | Host
Second draft of Communications Plan due to NCFE for review | 2022-02-01 | Host
Second draft of 2022 Event Guide due to NCFE for review | 2022-03-01 | Host
Final draft of Communications Plan due to NCFE for implementation | 2022-03-01 | Host
Final draft of 2022 Event Guide due to NCFE for approval (ready to post to web on 4/15/22) | 2022-04-01 | Host
2022 Event Guide posted to NCFE website | 2022-04-15 | NCFE
Invitation to VIP guests (sponsors, partners, etc.) to participate in Opening/Closing ceremonies | 2022-05-01 | Host/NCF
First draft Opening and Closing program agendas due to NCFE for approval | 2022-06-01 | Host/NCF
Final draft Opening and Closing program agendas due to NCFE for approval | 2022-07-01 | Host/NCF
Host 2022 Event | July 24-30, 2022 | Host/NCFE
Thank you letters to all Sponsors | 8/1/2022 - 8/15/2022 | Host/NCFE
Year Following Competition | September 1, 2022 - March 1, 2023